## Overview
COREOS / Feature Planning
PRODUCT BLUEPRINT • DRAFT 1.0 • 16 OCT 2026
14 modules · 79 capabilities · make-to-order manufacturing · R0–R3 delivery roadmap
Total capabilities | Modules | R0 MVP | R1 Connected | R2 Intelligence | R3 Advanced | Roadmap
79 | 14 | 36 | 24 | 12 | 7 | Scope per release, not calendar dates
PRODUCT PRINCIPLES
01 Order-to-delivery truth: order -> job -> operation -> event -> QC -> shipment
02 Kanban is one visualization, not the business data model
03 Verified skill + mandatory certification + calendar + machine capacity determine eligibility
04 Draft schedules are distinct from published schedules; no unsafe double booking
05 LLM explains and drafts; deterministic services validate; people approve high-impact changes
06 MVP excludes full ERP, payroll, IoT, autonomous QC and marketplace
07 All target KPI uplifts are pilot hypotheses pending baseline and validation
HOW TO USE THE WORKBOOK
Feature Backlog: backlog master with stable IDs for Jira/Trello issue creation.
Tech Scheduling: workstreams with technician skill/source of truth and scheduling gates.
Acceptance Tests: release-gating tests, with phase and system impact.
Release Plan: scope, dependencies and exit gates.
Roles & Access / KPI & Risks / Data Model / Decisions: implementation supporting tabs.

## Feature Backlog
FEATURE BACKLOG / 79 CAPABILITIES
MASTER INVENTORY • FILTER BY MODULE, PHASE, ROLE
Each row is a deliverable capability; P0 is the R0 operational MVP, P3 is the long-term expansion.
ID | Module | Capability | Detailed definition | Release | Priority | Primary role | Complexity | Depends on | Acceptance / verifiability | Target screen | Engine type | Delivery status
PLT-01 | PLT | Tenant & facility | Isolation tenant, multi-facility master; site-specific timezone and calendar. | R0 | P0 | Platform Admin | L |  | Different tenant cannot read/write another tenant record. | Admin / Tenant | Rules | Planned
PLT-02 | PLT | Users, roles & permissions | RBAC and site-scoped access; customer portal separate access. | R0 | P0 | Admin | M |  | Unauthorized role receives denied access on API and UI. | Admin / Access | Rules | Planned
PLT-03 | PLT | Audit & append-only business events | Capture actor, timestamp, before/after, reason and correlation ID. | R0 | P0 | Auditor | L |  | Material changes can be traced by job and actor. | Activity Log | Rules | Planned
PLT-04 | PLT | Configurable units & reference data | Units, shifts, stage labels, issue reasons, priority and terminology. | R0 | P0 | Admin | M |  | Validate core behavior, access, and audit in module test | Admin / Settings | Rules | Planned
PLT-05 | PLT | Notifications & inbox | In-app notifications for blockers, approvals, release and dispatch. | R0 | P0 | All staff | M |  | Validate core behavior, access, and audit in module test | Inbox | Rules | Planned
ORD-01 | ORD | Customer & order intake | Capture customer order, delivery address, promised date, attachments. | R0 | P0 | Sales | M |  | Order saved with item, qty and date validations. | Orders / Create | Rules | Planned
ORD-02 | ORD | Order items & partial jobs | One order may have many items, batches and production jobs. | R0 | P0 | Sales/PPIC | L | ORD-01 | Validate core behavior, access, and audit in module test | Orders / Detail | Rules | Planned
ORD-03 | ORD | Order health and milestones | Surface verified current milestone, material/QC state and escalation. | R0 | P0 | Sales/Owner | M | ORD-02 | Validate core behavior, access, and audit in module test | Orders / Detail | Rules | Planned
ORD-04 | ORD | Change request & revision | Record changes, affected documents and approvals; immutable releases. | R1 | P1 | Sales/Engineering | L | ENG-03,WFL-04 | Validate core behavior, access, and audit in module test | Orders / Changes | Rules | Planned
ORD-05 | ORD | Partial shipment & delivery close | Record delivered quantities, proof of delivery and open balance. | R1 | P1 | Logistics | M | ORD-02,QLT-02 | Validate core behavior, access, and audit in module test | Orders / Delivery | Rules | Planned
WFL-01 | WFL | Template builder | Create stage/node-based manufacturing template and validation. | R0 | P0 | Process Engineer | L |  | New jobs instantiate a published template version. | Workflow / Studio | Rules | Planned
WFL-02 | WFL | Dependencies and parallel nodes | Define prerequisites and parallel operations; reject invalid cycles. | R0 | P0 | Process Engineer | L | WFL-01 | Validate core behavior, access, and audit in module test | Workflow / Studio | Rules | Planned
WFL-03 | WFL | Versioned workflow instance | Pin job to published version, track execution state per operation. | R0 | P0 | PPIC | L | WFL-01,ORD-02 | Validate core behavior, access, and audit in module test | Production / Job | Rules | Planned
WFL-04 | WFL | Approval & gated transition | Require engineering/QC signoff and evidence before transitions. | R0 | P0 | Supervisor | L | WFL-03 | Validate core behavior, access, and audit in module test | Approvals / Inbox | Rules | Planned
WFL-05 | WFL | Conditional route and rework loop | Explicit branch after inspection and controlled rework return path. | R1 | P1 | Process Engineer | L | WFL-02,QLT-03 | Validate core behavior, access, and audit in module test | Workflow / Studio | Rules | Planned
WFL-06 | WFL | Custom operation forms | Required fields, attachments, numeric measurements on nodes. | R1 | P1 | Process Engineer | M | WFL-01 | Validate core behavior, access, and audit in module test | Workflow / Studio | Rules | Planned
ENG-01 | ENG | Technical documents | Drawing, product specification, attachments with secure access. | R0 | P0 | Eng Design | M |  | Validate core behavior, access, and audit in module test | Engineering / Documents | Rules | Planned
ENG-02 | ENG | Routing and standard time | Define operations, required skill, work center and base durations. | R0 | P0 | Eng Process | L | WFL-01 | Validate core behavior, access, and audit in module test | Engineering / Routing | Rules | Planned
ENG-03 | ENG | Document release & revision | Draft / review / released / superseded; freeze on job. | R0 | P0 | Eng Design | L | ENG-01 | Validate core behavior, access, and audit in module test | Engineering / Release | Rules | Planned
ENG-04 | ENG | BOM and material requirements | Link bill of materials with operation-specific consumption. | R0 | P0 | Eng Process | L | ENG-02 | Validate core behavior, access, and audit in module test | Engineering / BOM | Rules | Planned
ENG-05 | ENG | Engineering change impact | Trace impact of revision on open jobs, materials and QC. | R1 | P1 | Engineering | L | ENG-03,ORD-04 | Validate core behavior, access, and audit in module test | Engineering / Changes | Rules | Planned
MAT-01 | MAT | Material readiness per job | Required, available, shortage and expected arrival per operation. | R0 | P0 | Warehouse/PPIC | M | ENG-04 | Validate core behavior, access, and audit in module test | Materials / Readiness | Rules | Planned
MAT-02 | MAT | Shortage and blocker registry | Issue type, expected resolution, owner and impacted operation. | R0 | P0 | Warehouse | M | MAT-01 | Validate core behavior, access, and audit in module test | Materials / Issues | Rules | Planned
MAT-03 | MAT | Reservation and consumption | Reserve material and record consumption with stock integration optional. | R1 | P1 | Warehouse | L | MAT-01,INT-01 | Validate core behavior, access, and audit in module test | Materials / Reservation | Rules | Planned
MAT-04 | MAT | Substitute approval | Engineering approval for approved alternative materials. | R1 | P1 | Engineering | M | ENG-04,ORD-04 | Validate core behavior, access, and audit in module test | Materials / Substitution | Rules | Planned
RES-01 | RES | Technician profile | Employee code, team, primary site, active status, work center. | R0 | P0 | Supervisor/HR | M |  | Inactive technician cannot receive a new assignment. | People / Technicians | Rules | Planned
RES-02 | RES | Skill catalog | Skill code, category, description, skill levels 0-4, required evidence. | R0 | P0 | Supervisor | M | RES-01 | Validate core behavior, access, and audit in module test | People / Skills | Rules | Planned
RES-03 | RES | Verified technician skill matrix | Self-reported, observed, verified level; reviewer/date/evidence. | R0 | P0 | Supervisor | L | RES-02 | Only verified skill level counts toward eligibility. | People / Skill Matrix | Rules | Planned
RES-04 | RES | Certification & authorization | Machine or process authorization, expiry, hard-stop policy. | R0 | P0 | Supervisor/HSE | L | RES-01 | Expired mandatory certificate blocks assignment. | People / Qualifications | Rules | Planned
RES-05 | RES | Skill expiry and reassessment | Expiring qualifications, review cycle and alerts. | R1 | P1 | Supervisor | M | RES-03,RES-04 | Validate core behavior, access, and audit in module test | People / Qualifications | Rules | Planned
RES-06 | RES | Work center & machine catalog | Work centers, machine capabilities, maintenance state, capacity. | R0 | P0 | Plant Admin | M |  | Validate core behavior, access, and audit in module test | Resources / Machines | Rules | Planned
RES-07 | RES | Shift templates & weekly rosters | Day/night shifts, breaks, recurring patterns, paid/working time. | R0 | P0 | Supervisor | L |  | Calendar returns valid working intervals excluding breaks. | Resources / Shifts | Rules | Planned
RES-08 | RES | Availability exceptions | Leave, training, holidays, temporary unavailable, scheduled downtime. | R0 | P0 | Supervisor | M | RES-07 | Validate core behavior, access, and audit in module test | Resources / Calendar | Rules | Planned
RES-09 | RES | Overtime policy and approval | Overtime allowed by role, limit, explicit request and approval. | R1 | P1 | Supervisor | M | RES-07,WFL-04 | Validate core behavior, access, and audit in module test | Resources / Calendar | Rules | Planned
RES-10 | RES | Competency gap dashboard | Compare planned work demand hours vs qualified capacity hours. | R2 | P2 | Owner/PPIC | L | RES-03,SCH-04 | Validate core behavior, access, and audit in module test | People / Capacity | Rules | Planned
RES-11 | RES | Technician performance history | Durations, rework observations and scope-safe trends. | R2 | P2 | Supervisor | M | SFL-03,QLT-03 | Validate core behavior, access, and audit in module test | People / Profile | Rules | Planned
SCH-01 | SCH | Operations dispatch queue | Ready / waiting / blocked operations with prerequisites. | R0 | P0 | PPIC | L | WFL-03,ENG-02,MAT-01 | Validate core behavior, access, and audit in module test | Planning / Dispatch | Rules | Planned
SCH-02 | SCH | Manual technician assignment | Assign qualified technician to operation with time slot. | R0 | P0 | PPIC | L | RES-03,RES-04,RES-07,SCH-01 | Validate core behavior, access, and audit in module test | Planning / Assignment | Rules | Planned
SCH-03 | SCH | Machine and staff conflict detection | Validate overlapping reservations, site calendars and capacity. | R0 | P0 | PPIC | L | SCH-02,RES-06,RES-08 | No confirmed double-booking of non-shareable resources. | Planning / Calendar | Rules | Planned
SCH-04 | SCH | Capacity board | Daily/weekly capacity and workload by skill, machine, work center. | R1 | P1 | PPIC | L | SCH-03 | Validate core behavior, access, and audit in module test | Planning / Capacity | Rules | Planned
SCH-05 | SCH | Gantt schedule & drag reschedule | Manual timeline edits with immediate prerequisite validation. | R1 | P1 | PPIC | L | SCH-03 | Validate core behavior, access, and audit in module test | Planning / Timeline | Rules | Planned
SCH-06 | SCH | Schedule draft, publish and revision | Tentative drafts vs confirmed plan, version and affected staff notification. | R1 | P1 | PPIC | L | SCH-03,PLT-05 | Validate core behavior, access, and audit in module test | Planning / Publish | Rules | Planned
SCH-07 | SCH | Recommended eligible technicians | Rank eligible candidates by slack, travel/work center and workload; show reasons. | R2 | P2 | PPIC | L | RES-03,RES-04,SCH-03 | Validate core behavior, access, and audit in module test | Planning / Recommendations | Optimization | Planned
SCH-08 | SCH | Finite capacity scheduling | Constraint-aware scheduling based on actual skills, material, machine, shift. | R2 | P2 | PPIC | XL | SCH-04,SCH-06 | Validate core behavior, access, and audit in module test | Planning / Optimize | Optimization | Planned
SCH-09 | SCH | What-if recovery scenarios | Compare overtime, alternative routing and split batch with approval. | R3 | P3 | PPIC/Owner | XL | SCH-08,AII-04 | Validate core behavior, access, and audit in module test | Planning / Scenarios | Optimization | Planned
SFL-01 | SFL | Mobile task list | Technician sees assigned tasks, instructions, readiness and QR. | R0 | P0 | Technician | M | SCH-02,ENG-03 | Validate core behavior, access, and audit in module test | Workstation / Today | Rules | Planned
SFL-02 | SFL | Start, pause, resume, finish | Capture intervals and reason-coded pause/blocked states. | R0 | P0 | Technician | L | SFL-01 | Validate core behavior, access, and audit in module test | Workstation / Job | Rules | Planned
SFL-03 | SFL | Production quantity log | Good, reject, rework-in and rework-out with quantity safeguards. | R0 | P0 | Technician | L | SFL-01 | Counts cannot exceed available WIP and are not double-counted. | Workstation / Report | Rules | Planned
SFL-04 | SFL | Issues and photographic evidence | Record blockers, photos, annotated issue and responsible owner. | R0 | P0 | Technician | M | SFL-01 | Validate core behavior, access, and audit in module test | Workstation / Issues | Rules | Planned
SFL-05 | SFL | QR work order scan | Scan job/operation identifier to open permitted workstation action. | R0 | P0 | Technician | M | SFL-01 | Validate core behavior, access, and audit in module test | Workstation / Scan | Rules | Planned
SFL-06 | SFL | Offline queue and idempotent sync | Queue allowed events offline, conflict review upon reconnect. | R1 | P1 | Technician | XL | SFL-02,SFL-03 | Validate core behavior, access, and audit in module test | Workstation / Offline | Rules | Planned
QLT-01 | QLT | Inspection checklist & measurements | Versioned QC plan, required numeric readings and evidence. | R0 | P0 | QC | L | ENG-03,WFL-04 | Validate core behavior, access, and audit in module test | Quality / Inspect | Rules | Planned
QLT-02 | QLT | Accepted quantity and QC release | Accept/reject recorded quantity before release to delivery. | R0 | P0 | QC | L | QLT-01,SFL-03 | Validate core behavior, access, and audit in module test | Quality / Release | Rules | Planned
QLT-03 | QLT | NCR and rework | Nonconformance cause, ownership, corrective action, re-inspection. | R1 | P1 | QC/Supervisor | L | QLT-01 | Validate core behavior, access, and audit in module test | Quality / NCR | Rules | Planned
QLT-04 | QLT | Lot, batch and serial genealogy | Materials, jobs, operators, QC and deliveries link to tracked unit/batch. | R1 | P1 | QC | XL | MAT-03,SFL-03,QLT-02 | Validate core behavior, access, and audit in module test | Quality / Passport | Rules | Planned
QLT-05 | QLT | Digital product passport | Authorized customer-readable product manufacturing trail. | R3 | P3 | Customer/QC | L | QLT-04,CUS-01 | Validate core behavior, access, and audit in module test | Customer / Passport | Rules | Planned
CUS-01 | CUS | Read-only customer order milestones | Permissioned timeline, estimates labeled as estimates. | R0 | P0 | Customer | L | ORD-03,PLT-02 | Validate core behavior, access, and audit in module test | Portal / My Orders | Rules | Planned
CUS-02 | CUS | Customer approvals | Drawing/changes approval with identity, timestamp, audit. | R1 | P1 | Customer | L | ENG-03,ORD-04 | Validate core behavior, access, and audit in module test | Portal / Approvals | Rules | Planned
CUS-03 | CUS | Documents and shipment details | Share eligible QC reports, shipments, proof of delivery. | R1 | P1 | Customer | M | ORD-05,QLT-02 | Validate core behavior, access, and audit in module test | Portal / Documents | Rules | Planned
CUS-04 | CUS | Customer change requests | Submit requests, notify engineering, no direct schedule mutation. | R2 | P2 | Customer | L | ORD-04,CUS-02 | Validate core behavior, access, and audit in module test | Portal / Change Request | Rules | Planned
CMD-01 | CMD | Operations overview dashboard | Due, blocked, at-risk, workload; deep-link into evidence. | R1 | P1 | Owner/Supervisor | M | ORD-03,SCH-03,QLT-02 | Validate core behavior, access, and audit in module test | Command Center | Rules | Planned
CMD-02 | CMD | Exception inbox | Prioritize delayed material, absent qualified staff, resource conflicts. | R1 | P1 | PPIC/Owner | L | MAT-02,SCH-03 | Validate core behavior, access, and audit in module test | Command Center / Issues | Rules | Planned
CMD-03 | CMD | Baseline operational KPIs | OTD, lead-time variance, FPY, backlog, reporting completeness. | R1 | P1 | Owner | M | SFL-03,QLT-02,ORD-05 | Validate core behavior, access, and audit in module test | Analytics | Rules | Planned
AII-01 | AII | Production-context assistant | Read-only Q&A with role filtering, evidence links and missing-data caveats. | R1 | P1 | Manager | L | PLT-02,ORD-03,PLT-03 | Validate core behavior, access, and audit in module test | CoreAI / Assistant | AI | Planned
AII-02 | AII | Risk rules and explanation | Detect potential lateness and explain blockers deterministically. | R1 | P1 | PPIC | L | SCH-03,MAT-02,ORD-03 | Validate core behavior, access, and audit in module test | CoreAI / Risk | Hybrid | Planned
AII-03 | AII | RFQ/document extraction draft | Draft specs and questions from uploaded files, engineer reviews output. | R2 | P2 | Engineering | L | ENG-01 | Validate core behavior, access, and audit in module test | CoreAI / Document | AI | Planned
AII-04 | AII | Promise Engine | Calculate candidate delivery date based on finite-capacity constraints. | R2 | P2 | Sales/PPIC | XL | SCH-08,ORD-02 | Validate core behavior, access, and audit in module test | CoreAI / Promise | Optimization | Planned
AII-05 | AII | Factory memory and similar jobs | Evidence-backed prior job lookup and duration benchmarks. | R2 | P2 | Engineering/PPIC | L | SFL-03,QLT-03 | Validate core behavior, access, and audit in module test | CoreAI / Memory | AI | Planned
AII-06 | AII | Recovery copilot | Propose ranked recovery plans but execute only upon explicit approval. | R3 | P3 | PPIC | XL | SCH-09,AII-02 | Validate core behavior, access, and audit in module test | CoreAI / Recovery | Hybrid | Planned
AII-07 | AII | Camera-assisted visual QC | Assisted anomaly detection with human verification and test protocol. | R3 | P3 | QC | XL | QLT-01 | Validate core behavior, access, and audit in module test | CoreAI / Vision | AI | Planned
CST-01 | CST | Estimated standard job cost | Material, labor, machine and outsourced budget per operation. | R2 | P2 | Owner/Costing | L | ENG-04,ENG-02 | Validate core behavior, access, and audit in module test | Cost / Estimates | Rules | Planned
CST-02 | CST | Actual vs estimated variance | Accumulate actual hours, material, scrap and rework costs. | R2 | P2 | Owner/Costing | L | CST-01,SFL-02,QLT-03 | Validate core behavior, access, and audit in module test | Cost / Variance | Rules | Planned
CST-03 | CST | Margin leakage explanation | Highlight large variances with supporting records. | R3 | P3 | Owner | L | CST-02 | Validate core behavior, access, and audit in module test | Cost / Intelligence | Hybrid | Planned
INT-01 | INT | Public API and inbound import | Versioned API/CSV import for orders, material and identities. | R1 | P1 | IT/Admin | L |  | Validate core behavior, access, and audit in module test | Integrations / API | Rules | Planned
INT-02 | INT | Outbound webhooks | Signed and retryable production events with tenant-safe payloads. | R1 | P1 | IT/Admin | L | PLT-03 | Validate core behavior, access, and audit in module test | Integrations / Webhooks | Rules | Planned
INT-03 | INT | Email/WA notification connectors | Configurable outbound channels with consent and delivery logs. | R2 | P2 | Admin | L | PLT-05 | Validate core behavior, access, and audit in module test | Integrations / Channels | Rules | Planned
INT-04 | INT | HRIS/absence integration | Import eligible leave and shift changes; keep source-of-truth rules. | R2 | P2 | HR/Admin | L | RES-08,INT-01 | Validate core behavior, access, and audit in module test | Integrations / HRIS | Rules | Planned
INT-05 | INT | IoT machine telemetry | Optional machine downtime/events bridge, manual fallback. | R3 | P3 | Plant IT | XL | RES-06,INT-02 | Validate core behavior, access, and audit in module test | Integrations / Machines | Rules | Planned
INT-06 | INT | Cross-factory subcontract exchange | Explicit opt-in external capacity collaboration. | R3 | P3 | Owner | XL | SCH-09,PLT-02 | Validate core behavior, access, and audit in module test | Network / Partner | Rules | Planned

## Tech Scheduling
TECHNICIAN + RESOURCE SCHEDULING
DESIGN DEEP DIVE • RES/SCH
Explicit source-of-truth, booking constraints and transition governance for technician assignment.
Domain | Feature ID | Primary data | Source of truth | Eligibility rule / behavior | User-facing surface | Phase
People & Resource Capability | RES-01 | Technician profile | HR / Supervisor | Active employment, facility and site validation | People / Technicians | R0
People & Resource Capability | RES-02 | Skill catalog | Process engineer | Skill taxonomy, level meanings and evidence policy | People / Skills | R0
People & Resource Capability | RES-03 | Verified technician skill matrix | Supervisor | Verified level only; self-declared is advisory | People / Skill Matrix | R0
People & Resource Capability | RES-04 | Certification & authorization | HSE / Supervisor | Credential valid during FULL assignment; mandatory hard stop | People / Qualifications | R0
People & Resource Capability | RES-05 | Skill expiry and reassessment | Supervisor | Notify expiry before assigned operation starts | People / Qualifications | R1
People & Resource Capability | RES-06 | Work center & machine catalog | Plant admin | Machine capacity, compatibility and maintenance state | Resources / Machines | R0
People & Resource Capability | RES-07 | Shift templates & weekly rosters | Supervisor / Roster system | Published shift working windows exclude breaks | Resources / Shifts | R0
People & Resource Capability | RES-08 | Availability exceptions | Supervisor / HRIS | Leave/training/holiday overrides shift availability | Resources / Calendar | R0
People & Resource Capability | RES-09 | Overtime policy and approval | Supervisor | OT only after policy + approval | Resources / Calendar | R1
People & Resource Capability | RES-10 | Competency gap dashboard | Scheduler | Qualified demand hours vs eligible free time | People / Capacity | R2
People & Resource Capability | RES-11 | Technician performance history | Shop-floor event store | Historical work informs reviews, never auto-certification | People / Profile | R2
Planning & Scheduling | SCH-01 | Operations dispatch queue | Job + material + workflow | Operation eligible only after all prerequisites | Planning / Dispatch | R0
Planning & Scheduling | SCH-02 | Manual technician assignment | PPIC | Manual assignment with mandatory eligibility validation | Planning / Assignment | R0
Planning & Scheduling | SCH-03 | Machine and staff conflict detection | Resource reservations | No overlap for exclusive people/machines | Planning / Calendar | R0
Planning & Scheduling | SCH-04 | Capacity board | Calendar/reservation engine | Capacity by qualification, shift and work center | Planning / Capacity | R1
Planning & Scheduling | SCH-05 | Gantt schedule & drag reschedule | PPIC | Drag to reschedule; revalidate on commit | Planning / Timeline | R1
Planning & Scheduling | SCH-06 | Schedule draft, publish and revision | PPIC | Draft vs published plan and version trail | Planning / Publish | R1
Planning & Scheduling | SCH-07 | Recommended eligible technicians | Rank engine | Filter hard constraints before ranking eligible technicians | Planning / Recommendations | R2
Planning & Scheduling | SCH-08 | Finite capacity scheduling | Finite capacity solver | Optimize constraints not LLM arithmetic | Planning / Optimize | R2
Planning & Scheduling | SCH-09 | What-if recovery scenarios | Optimizer + approver | What-if produces proposals; requires approval | Planning / Scenarios | R3

## Acceptance Tests
ACCEPTANCE & BUSINESS RULE TESTS
TEST STRATEGY • GATE BEFORE RELEASE
Core qualification and resource booking are non-negotiable server-side controls.
ID | Phase | Area | Given context | When action | Expected outcome
AC-01 | R0 | Skills | Technician lacks VERIFIED Welding L3 | PPIC publishes Welding L3 job | Reject publish: unverified skill; show missing requirement
AC-02 | R0 | Certification | Credential expires at 15:00 | Assignment spans 14:00–16:00 | Reject publish: certificate not valid across entire slot
AC-03 | R0 | Shift | Shift 08:00–16:00 with break 12:00–13:00 | Plan 4 contiguous working hours | Exclude break; no invalid 11:00–15:00 uninterrupted booking
AC-04 | R0 | Availability | Technician has approved leave | Assign overlapping leave | Reject: unavailable calendar interval
AC-05 | R0 | Machine | Exclusive welding machine booked | Book another overlapping job | Reject prohibited resource overlap
AC-06 | R0 | Concurrency | Two PPICs attempt conflicting publish | Concurrent commit | At most one confirmed reservation
AC-07 | R0 | Readiness | Drawing not released or predecessor incomplete | Dispatch job | Block dispatch and show missing prerequisite
AC-08 | R0 | Quantity | Operation WIP 10 units | Submit 12 good and 3 reject | Reject excess and preserve audit trail
AC-09 | R1 | Quality | Operation complete but QC fails | Initiate rework | Create linked rework flow without double counting
AC-10 | R0 | Revision | Job pinned to drawing REV-02 | Engineer releases REV-03 | Active job keeps REV-02 until change approval
AC-11 | R0 | Security | Customer account A | Guess B order URL/API ID | Deny access independent of client UI
AC-12 | R1 | Offline | Event sent twice with same idempotency key | Sync twice | Apply exactly once to quantity projection
AC-13 | R1 | Schedule version | Published schedule changes | Reschedule a job | Keep prior plan, reason, notifications
AC-14 | R2 | AI | No reliable operation history | Ask for predicted completion | State insufficient data; bounded estimate only if assumptions known
AC-15 | R2 | AI controls | AI suggests unqualified staff | Planner approves suggestion | Hard qualification API gate still rejects

## Release Plan
RELEASE ROADMAP
RELEASE GATES • NO CALENDAR ASSUMPTIONS
Release ordering reflects dependencies; no delivery date or effort estimate is asserted.
Release | Priority | Feature count | Outcome | Exit gate | Risks / prerequisites
R0 Operational MVP | P0 | 36 | Order to job to workflow and qualified manual dispatch, shop-floor events, QC gates, read-only portal | Evidence-complete order trace, quality reconciliation, safe technician/machine assignment, tenant isolation | Facility+skill setup; operators willing to use workstation
R1 Connected | P1 | 24 | Capacity board, schedule publication, change control, alerts, NCR/traceability, API and dashboards | Pilot site uses system daily; customer-visible milestones validated; exception rules audited | Good R0 event completeness and site calendars
R2 Intelligent | P2 | 12 | Smart technician suggestions, finite scheduling, Promise Engine, factory memory and costing | Measured estimator backtest; constraints + assumptions explained and approved | Standard times, enough trustworthy history
R3 Adaptive | P3 | 7 | Recovery scenarios, visual QC, IoT, digital passport, cross-factory network | Separate risk/safety/privacy validation for each advanced feature | Specific manufacturing pilot, integrations and governance
RELEASE DEPENDENCY CHAIN
R0: source-of-truth events, workflows, qualifications, manual safe bookings
R1: published schedule and material/QC/customer linkage + risk rules
R2: quality historical data -> constraint solver -> feasible delivery recommendation
R3: scenario approval -> controlled recovery and extended ecosystem

## Roles & Access
ROLES & ACCESS
PERSONA MAP
Access is checked at API/service level as well as in the UI. R0 client/customer is deliberately restricted.
Role | Job to be done | Non-negotiable boundary
Platform Admin | Multi-tenant provisioning, security, billing boundary | No operational cross-tenant data by default
Tenant Admin | Users, access, configuration, site controls | Full config in assigned tenant
Owner/Director | Operational oversight, risks, approvals | Read business summaries and authorized costs
Sales/CS | Orders, customer milestones, change requests | Cannot bypass engineering/QC release
Engineering Design | Drawing, revision, approval | Released drawing immutable
Engineering Process | BOM, routing, required skills/time | Cannot self-approve when segregation policy applies
PPIC/Planner | Dispatch, schedule, resource allocation | Cannot assign unqualified technician
Warehouse/Purchasing | Material availability, shortages | No unauthorized editing of released BOM
Supervisor | Technician verification, shifts, exceptions | Audit skill/availability edits
Technician | Assigned work, events, issue evidence | Own jobs; no schedule override
QC | Inspection, NCR, acceptance | Independent final release if configured
Customer | Shared orders, documents and approval | No internal jobs, margin or technician PII

## KPIs & Risks
KPIs & RISKS
BUSINESS MEASUREMENT
Targets are pilot hypotheses requiring a baseline; they are not achieved outcomes.
KPI ID | Measure | Formula | Owner | Cadence | Pilot hypothesis | Phase
KPI-01 | On-time delivery | Delivered on/before confirmed promise / delivered orders | Owner / Sales | Monthly | Target pilot: +10 percentage points versus baseline | R1
KPI-02 | Plan adherence | Operations completed within published plan window / planned operations | PPIC | Weekly | Target pilot: establish baseline and improve | R1
KPI-03 | Lead-time variance | Actual lead time minus planned lead time in days | Owner / PPIC | Monthly | Target pilot: -20% average absolute variance | R1
KPI-04 | First-pass yield | Units passing initial inspection / units inspected first time | QC | Weekly | Target pilot: establish baseline and improve | R1
KPI-05 | Blocker resolution time | Average time between blocker opened and resolved | Supervisor | Weekly | Target pilot: -20% vs baseline | R1
KPI-06 | Shop-floor event timeliness | Required events captured within current shift / expected events | Supervisor | Weekly | Target pilot: >=95% | R0
KPI-07 | Qualification compliance | Assignments of restricted operations with valid verified credentials / restricted assignments | HSE / PPIC | Daily | Target: 100% | R0
KPI-08 | Scheduling conflict prevention | Confirmed assignments free of prohibited technician/machine overlaps / confirmed assignments | PPIC | Daily | Target: 100% | R0
KPI-09 | Customer status inquiry reduction | Comparative count of manual status requests per 100 orders | Sales | Monthly | Target pilot: -30% vs baseline | R1
KPI-10 | AI recommendation adoption | Approved suggestions / all suggestions shown | Product | Monthly | Learning metric; no contractual target | R2
Risk | Potential impact | Mitigation
Poor event coverage | AI and ETA unreliable | Make shop-floor input simple; completeness dashboard; do not claim precise ETAs
Over-customized process engine | Delivery slow, hard-to-maintain rules | Limit V1 nodes and review extension demand
Stale qualification records | Unqualified operator assignment | Verified-only eligibility, expiry hard stops, reassessment owners
Wrong double-booked resources | Production bottlenecks | Atomic reservation, overlap checks, published revisions
Customer sees internal or speculative data | Trust/privacy leak | Dedicated portal projections, RBAC, verified milestones, human-approved dates
AI hallucinated operational claims | Poor business decisions | Evidence citations, deterministic calculators, permission boundary
Offline duplicate sync | Inflated quantity/progress | Idempotency keys, server-side constraints, conflict review
Scope creep into ERP | Timeline and cost exceed budget | Integrate inventory/finance instead of rebuilding everything

## Data Model
LOGICAL DATA MODEL
DOMAIN ARCHITECTURE
Suggested entities; adapt naming to implementation conventions and existing schemas.
Domain | Primary entities | Key relationships / rule
Identity | tenants, facilities, users, roles, permissions | tenant_id at every boundary; site role scope
Orders | customers, orders, order_items, production_jobs, shipments | One order has many items; items may split into jobs; shipments partial
Workflow | workflow_templates, workflow_versions, nodes, edges, operation_instances | Jobs pinned to published workflow version; operation dependencies
Engineering | technical_documents, releases, bom_items, routings, routing_steps | Released documents linked to jobs; material and skill constraints
People | technicians, skill_catalog, skill_assessments, certificates, authorizations | Verified skill with reviewer + effective date; cert expires at slot end
Resources | work_centers, machines, shifts, rosters, calendar_exceptions | Working intervals computed from shift minus exceptions
Scheduling | schedule_versions, assignments, reservations, dispatch_events | Atomic publish and capacity-aware reservations
Execution | production_events, time_intervals, quantity_movements, issue_events | Append-only/idempotent quantity and time data
Quality | qc_plans, inspections, nonconformances, rework_orders, genealogy | Separate accepted, rejected, rework, delivered quantities
Customer | portal_accounts, portal_grants, customer_approvals, document_shares | No cross-customer access; only verified milestones
Intelligence | risk_signals, ai_runs, recommendations, proposal_approvals | Evidence references, scoring version, approval state
Audit | audit_events, notifications, integration_event_outbox | Actor, timestamp, reason, source, schema version and tenant

## Decisions
ARCHITECTURE DECISIONS
DRAFT DECISION LOG
Working assumptions to confirm with manufacturers before fixing API and schema contracts.
ID | Decision | Recommended default | Status
D-01 | Initial target segment | Discrete make-to-order / custom jobs; pilot with 1-2 manufacturers | Working assumption
D-02 | Operating model | Multi-tenant SaaS; can later add dedicated/on-prem | Recommended
D-03 | Site timezone | Facility timezone, default Asia/Jakarta; UTC timestamps in backend | Recommended
D-04 | Workforce truth | Supervisor-approved skill data; HRIS/shift calendar authoritative for availability | Required
D-05 | AI safety | AI recommends, not publishes irreversible plans or releases QC | Required
D-06 | Inventory scope | Readiness + reservations; full inventory ERP excluded for MVP | Recommended
D-07 | Process flexibility | Versioned workflow templates + fixed governance gates | Required
D-08 | MVP cutoff | R0 P0 features; R1 P1 connected, R2 P2 intelligence, R3 P3 moonshot | Working assumption